## QA Status Report
QA Status Report
| Defects Summary | [5 empty] | Open Issues
| Status/Severity | High | Med | Low | Total | % of Total | SlNo | Severity | Assigned | Test Case Id | Status
| New | 0 | 1 | 0 | 1 | 4% | 1 | High | Dolev | Bug 36882 | New
| Fixed | 0 | 2 | 0 | 2 | 8% | 2 | Medium | Dolev | Bug 36884 | Reopen
| Closed | 6 | 12 | 0 | 18 | 72%
| Reject | 0 | 0 | 0 | 0 | 0%
| Reopen | 0 | 4 | 0 | 4 | 16% | Defects Logged
| Total | 6 | 19 | 0 | 25 | 100% | Severity | Count | Defect ID
[7 empty] | High | 4 | Bug 36882
| Closed Issues |  |  | Retest Summary |  |  |  |  | Bug 36883
| SlNo | Test Case ID |  | Total Resolved | 14 |  |  |  | Bug 36884
| 1 | Bug 36882 |  | Total Re-opened | 4 |  |  |  | Bug 36885
| 2 | Bug 36883 |  | Total Closed | 18 |  | Medium | 2 | Bug 36886
|  |  |  | Total Not Tested | 0 |  |  |  | Bug 36887
[7 empty] | Low | 6 | Bug 36888
| Test Case Summary | [7 empty] | Bug 36889
| Modules | Total Number of test Cases | No of test cases executed | No of test Cases Passed | No of test Cases Failed |  |  |  | Bug 36890
| Initial Request Form | 24 | 15 | 8 | 5 |  |  |  | Bug 36891
| Verification Form | 31 | 20 | 9 | 6 |  |  |  | Bug 36892
| Customer Decision Form | 22 | 6 | 11 | 2 |  |  |  | Bug 36893
| Total | 77 | 41 | 28 | 13 |  | Total | 10